## Slide 1: Building a governed OneLake — on a fixed clock
A repeatable delivery blueprint for standing up Fabric OneLake with a Bronze → Silver → Gold medallion core, wrapped in governance, security, audit and DataOps from day one — scoped and priced by a transparent T-shirt sizing model.
July 2026
Microsoft Fabric
ERP · CRM
Files · APIs
Streams
Sources
Serve
ONELAKE · DELTA / PARQUET
Power BI
SQL / WH
AI / Agents
Bronze
Immutable landing · raw · append-only
Sliver
Cleansed · conformed · modelled
Gold
Curated KPIs · business-ready
Governance · Security · Audit
cross-cutting · every layer
One logical lake, three quality tiers, governance woven through every layer.
3
Sizing tiers
4
Scoping dimensions
8
Platform layers
1x
Build, N geographies

## Slide 2: Fixed scope, transparent sizing, governed from the first commit
Time-boxed programmes fail when scope is discovered late. We invert that: scope is declared up front against four measurable dimensions, mapped to a T-shirt size, and each size carries a pre-agreed team shape and timeline. Non-negotiable platform layers — governance, security, audit, DataOps — are built alongside the data, never bolted on after go-live.
Scope drives size, size drives plan
Sources, ingestion complexity, Silver tables and Gold KPIs are counted in discovery. Those counts deterministically select Simple, Medium or Complex — and with it the timeline, team and cost envelope.
Governance is a layer, not a phase
Domains, workspace roles, OneLake security, sensitivity labels and audit are stood up before the first table lands, so trust and lineage are properties of the platform — not remediation debt.
Build once, deploy everywhere
Metadata-driven, parameterized pipelines mean identical source systems across geographies are onboarded through configuration — not re-engineering. The framework is the deliverable.
Principle

## Slide 3: End-to-end target state on Microsoft Fabric
A single reference architecture scales across all three sizes; what changes is breadth (source count, table count, streaming) not shape. OneLake is the system-of-record; Delta Lake with V-Order is the storage standard; Direct Lake serves semantic models with no import refresh.
SAP · Oracle · Dynamics
Salesforce · SaaS APIs
Files · SFTP · ADLS · S3
Sources
DB (CDC) · Mirroring
Event streams · IoT
Data Factory
Pipelines · Copy job · Dataflows
Mirroring
Zero-ETL DB replication
Shortcuts
Zero-copy to ADLS/S3
Eventstream
Real-Time Intelligence
Ingestion
Bronze LH
Raw, immutable
Append-only
Full replay history
Ingestion metadata
Partition by load date
Sliver LH
Cleansed / typed
Conformed dims
Deduped · SCD
Data-quality gates
Business keys
Spark / Notebooks
T-SQL / Warehouse
Gold LH/WH
Star schemas
Aggregates / marts
KPI definitions
Certified datasets
Power BI
Excel · Teams
SQL endpoint
Copilot / Agents
Activator alerts
Eventhouse (KQL)
real-time landing
Bronze
Silver
Gold
Consumption
Semantic Model
Direct Lake · DAX
RLS / OLS applied
Governance
Domains · OneLake catalog · Purview lineage · endorsement · glossary
Security
Entra ID · workspace roles · OneLake security · RLS/CLS · labels · DLP
Audit & Observability
Domains · OneLake catalog · Purview lineage · endorsement · glossary
DATAOPS / CICD
Git integration · deployment pipelines (Dev→Test→Prod) · Variable Libraries · fabric-cicd · Key Vault
Orchestration
Metadata-driven control framework · scheduler · dependency & watermark management
Fabric Capacity (F-SKU / Capacity Units) · ONELAKE — single logical store · Delta + V-Order
Microsoft Entra Id · Tenant Settings · Private Networking · Key Vault
Reference architecture. The upper band is the medallion data path; the lower bands are the cross-cutting platform layers present in every engagement regardless of size.

## Slide 4: Eight layers. Everyone in scope, every size
The medallion tiers get the attention, but a production platform is defined by the layers around them.
Each is scaled — not skipped — as size increases.
L1
L2
L3
L4
L5
L6
L7
L8
Ingestion & Landing
Medallion Transformation (Bronze · Silver · Gold)
Metadata-Driven Orchestration
Governance & Data Catalog
Security & Access Control
Audit, Logging & Observability
DataOps & CI/CD
Data Quality & Reconciliation
Connectivity to source systems and reliable capture into Bronze. Batch and incremental via Data Factory pipelines and Copy job; zero-ETL via Mirroring; zero-copy via OneLake Shortcuts; real-time via Eventstream into an Eventhouse.
Bronze is an immutable, append-only audit trail. Silver cleanses, types, conforms and de-duplicates with data-quality gates. Gold curates star schemas, marts and KPI definitions consumed through Direct Lake semantic models.
A control framework of configuration tables drives generic, parameterized pipelines and notebooks — load type, watermark, dependencies, schedule and target mapping all live in metadata rather than in hand-built pipelines. This layer is what makes multi-geo reuse possible.
Domains and sub-domains structure ownership from tenant down to workspace. The OneLake catalog (Explore / Govern / Secure) drives discovery, endorsement (Promoted / Certified) and a governance-completeness backlog. Purview extends lineage, classification and enterprise-wide catalog.
Layered least-privilege: Entra ID groups → workspace roles (Admin/Member/Contributor/Viewer) → item permissions → OneLake security roles (folder/table) → row- and column-level security → dynamic data masking → sensitivity labels with DLP. Most users are restricted to Gold.
All user activity flows to the Purview audit log. Pipeline and notebook runs are captured for lineage and re-run; the Monitoring hub and Capacity Metrics app track jobs, failures and CU consumption. Custom run-logging into control tables gives an operational audit of every load.
Workspace-level Git integration (Azure DevOps / GitHub) with deployment pipelines promoting Dev → Test → Prod. Variable Libraries remove hard-coded references across environments; fabric-cicd and Fabric REST APIs enable code-first automated deployment and testing.
Quality rules enforced at the Silver gate (completeness, validity, uniqueness, referential integrity) with quarantine handling, plus source-to-target reconciliation counts and a DQ scorecard surfaced to data owners. Failures are logged, alerted and blocked from promotion.

## Slide 5: Four dimensions decide the size
Scope is measured, not estimated. Count the sources, classify ingestion complexity, count target Silver tables and Gold KPIs. The highest tier triggered across the four dimensions sets the size — one dimension in "Complex" pulls the whole engagement to Complex.
Scoping Dimension
Simple
≤5 sources · batch · ≤20 Silver · ≤25 KPIs
Medium
6–15 sources · batch+CDC · 21–60 Silver · 26–75 KPIs
Complex
15+ sources · streaming/CDC/MDM · 60+ Silver · 75+ KPIs
# Source systems
Ingestion complexity
# Silver tables
# Gold KPIs
MAX(tier)
Worst – case dimension wins
Fig 2. Sizing is a MAX() across dimensions — a single streaming or high-volume requirement legitimately escalates the tier.
Dimension | Simple Bronze tier | Medium Silver tier | Complex Gold tier
# Source systems | 1 – 5 | 6 – 15 | >15 upto 30
Ingestion complexity | Batch, well-structured; native connectors, Copy job, Mirroring. Minimal transform. | Batch + incremental / CDC; some APIs & semi-structured; moderate transforms & DQ. | Real-time / streaming + CDC + APIs + unstructured; heavy transforms, MDM, historical loads.
# Silver tables | ≤ 20 | 21 – 60 | 60-75
# Gold KPIs / measures | ≤ 25 | 26 – 75 | 75-90
Geography / domains | Single geo, single domain | Single geo (light multi-geo), multiple domains | Multi-geo, multi-domain, data residency & compliance
Indicative capacity | F8 – F16 | F16 – F64 | F64+ (multi-capacity)
Capacity SKUs are indicative starting points. Right-sizing is a workload calculation (refresh, query concurrency, pipeline volume) targeting ~60–70% sustained CU utilisation, validated with the Capacity Metrics app after go-live. F-SKUs run F2 through F2048; reserved 1-year capacity carries a material discount over pay-as-you-go.
Notes: Scope is measured, not estimated. Count the sources, classify ingestion complexity, count target Silver tables and Gold KPIs. The highest tier triggered across the four dimensions sets the size — one dimension in "Complex" pulls the whole engagement to Complex.

## Slide 6: Same sources, many regions? Build the factory, not the product
When the same source systems (regional ERP, CRM or POS instances) recur across geographies, hand-building a pipeline per region is waste and a maintenance liability. A metadata-driven framework onboards each new geography through configuration — identical code, different config — turning weeks of build into days of setup.
How the framework is realised in Fabric
Config over code. Source, entity, load-type, watermark, mapping and DQ rules live in control tables; a handful of generic pipelines and notebooks execute any entity by reading its config.
One codebase, many parameters. Variable Libraries inject geo-specific values (connections, schedules, residency) at deploy time — the artefacts are identical across regions.
Hub-and-spoke workspaces. A shared platform/framework workspace plus per-geo data workspaces, organized under Domains so ownership and policy cascade cleanly.
Data residency respected. Region-appropriate capacities; Shortcuts avoid unnecessary data movement while keeping a single logical OneLake view.
Promote, don't rebuild. Git integration + deployment pipelines + fabric-cicd push the same framework Dev→Test→Prod and into each geo.
Governance inherited. Domain-level sensitivity, DLP and endorsement policies cascade to every geo; local overrides only where compliance demands
Fig 3. One control plane feeds N geographies. New regions are configuration, not code.
Control Plane (build once)
Source registry
system · entity · load type
Mapping & DQ rules
target · watermark · rules
Geo / tenant params
region · residency · schedule
Generic pipelines
parameterized · config-driven
Parameterised notebooks
one codebase · all geos
Variable Libraries · fabric-cicd · Git
Geo · EMEA
config only · ~days
Geo · AMER
config only · ~days
Geo · APAC
config only · ~days
Economic effect. The first geography carries the framework build cost. Each subsequent geography onboards at a fraction of that — typically days of configuration and validation rather than a full rebuild — which is why multi-geo scope belongs in Complex but does not scale linearly with region count.

## Slide 7: What each size costs in time and people
Figures below are indicative planning estimates drawn from typical Fabric engagements and assume the readiness conditions in §07. Timelines are elapsed calendar duration with the team working in parallel workstreams.
Simple
Departmental / single-domain lakehouse
Medium
Cross-functional enterprise platform
Complex
Multi-geo, streaming, governed estate
T-shirt · Bronze tier
T-shirt · Sliver tier
T-shirt · Gold tier
Elapsed timeline | 6 – 8 wks ~1.5 – 2 months
Team size | 3 – 4 peak FTE
Total effort | ~5 – 7 person-months
Delivery shape | 1 pod single squad
Elapsed timeline | 10 – 16 wks ~2.5 – 4 months
Team size | 5 – 8 peak FTE
Total effort | ~15 – 23 person-months
Delivery shape | 1 – 2 pod parallel streams
Elapsed timeline | 5 – 9 mo ~20 – 36 wks
Team size | 9 – 15+ peak FTE
Total effort | ~45 – 90 person-months
Delivery shape | 2 - 3 pod + platform team

## Slide 8
Thank You
Follow Us:
www.syrencloud.com

## Slide 9: Eight layers. Everyone in scope, every size
The medallion tiers get the attention, but a production platform is defined by the layers around them.
Each is scaled — not skipped — as size increases.
L1
L2
L3
L4
L5
L6
L7
L8
Ingestion & Landing
Connectivity to source systems and reliable capture into Bronze. Batch and incremental via Data Factory pipelines and Copy job; zero-ETL via Mirroring; zero-copy via OneLake Shortcuts; real-time via Eventstream into an Eventhouse.
Medallion Transformation (Bronze · Silver · Gold)
Bronze is an immutable, append-only audit trail. Silver cleanses, types, conforms and de-duplicates with data-quality gates. Gold curates star schemas, marts and KPI definitions consumed through Direct Lake semantic models.
Metadata-Driven Orchestration
A control framework of configuration tables drives generic, parameterized pipelines and notebooks — load type, watermark, dependencies, schedule and target mapping all live in metadata rather than in hand-built pipelines. This layer is what makes multi-geo reuse possible.
Governance & Data Catalog
Domains and subdomains structure ownership from tenant down to workspace. The OneLake catalog (Explore / Govern / Secure) drives discovery, endorsement (Promoted / Certified) and a governance-completeness backlog. Purview extends lineage, classification and enterprise-wide catalog.
Security & Access Control
Layered least-privilege: Entra ID groups → workspace roles (Admin/Member/Contributor/Viewer) → item permissions → OneLake security roles (folder/table) → row- and column-level security → dynamic data masking → sensitivity labels with DLP. Most users are restricted to Gold.
Audit, Logging & Observability
All user activity flows to the Purview audit log. Pipeline and notebook runs are captured for lineage and re-run; the Monitoring hub and Capacity Metrics app track jobs, failures and CU consumption. Custom run-logging into control tables gives an operational audit of every load.
DataOps & CI/CD
Workspace-level Git integration (Azure DevOps / GitHub) with deployment pipelines promoting Dev → Test → Prod. Variable Libraries remove hard-coded references across environments; fabric-cicd and Fabric REST APIs enable code-first automated deployment and testing.
Data Quality & Reconciliation
Quality rules enforced at the Silver gate (completeness, validity, uniqueness, referential integrity) with quarantine handling, plus source-to-target reconciliation counts and a DQ scorecard surfaced to data owners. Failures are logged, alerted and blocked from promotion.

## Slide 10: Ideal resource mix
Bars show relative FTE weighting within each team; the figure on the right is the indicative headcount for that role at peak.
Simple · 3–4 FTE
Medium · 5–8 FTE
Complex · 9–15+ FTE
Data Platform Architect part-time, shared | 0.5
Data Engineer pipelines + Spark | 1 – 2
Analytics / BI Engineer Gold + semantic model | 1
Delivery lead / PM part-time | 0.25
Data Platform Architect | 1
Data Engineer | 2 – 3
Analytics / BI Engineer | 1 – 2
Governance / Security part-time specialist | 0.5
QA / DataOps Engineer | 0.5 – 1
Delivery lead / Scrum | 0.5 – 1
Lead / Solution Architect | 1 – 2
Data Engineers across pods | 4 – 6
Analytics / Semantic modellers | 2 – 3
RTI / Streaming Engineer | 1
Governance & Security dedicated | 1
Platform / DevOps Engineer | 1
QA / DataOps | 1
Business Analyst(s) | 1 – 2
Delivery / Programme Manager | 1
Governance & security handled by the architect using platform defaults; DataOps set up once at the start.
Business analyst / data SMEs engaged from the client side for source mapping and KPI definition.
Organized as 2–3 delivery pods over a shared platform team owning the reusable framework, security and CI/CD.

## Slide 11: Where the estimates come from — and what could move them
The timelines and team sizes above are planning estimates based on typical Fabric engagements. They are not commitments until scope is confirmed. These are the conditions they assume and the questions discovery resolves.
Estimates assume
Fabric capacity and licensing are provisioned or procured before mobilization.
Source systems are accessible with credentials and, where needed, network/private connectivity in place.
Client data SMEs are available for source mapping, KPI definition and UAT.
Source data is of reasonable, documented quality; heavy remediation or MDM is called out separately.
KPI and semantic-model definitions are agreed early (or a discovery slot is allocated to define them).
A single tenant with agreed governance and tenant-setting ownership.
Discovery confirms & can shift size
Actual data volumes and refresh frequency (drives capacity and can raise the tier).
Real ingestion complexity per source — CDC, streaming, unstructured, API rate limits.
Number and volatility of Silver tables and Gold KPIs once mapped.
Compliance / data-residency obligations per geography.
Historical / backfill load requirements and cutover strategy.
Organizational readiness: existing DataOps maturity, security model, approvals.
Honest framing. This proposal is a delivery blueprint and sizing model, not a fixed bid. The sizing thresholds, timelines and team shapes reflect common patterns; your figures may differ. We recommend a short-paid discovery to count the four dimensions against your real estate before committing to a size and price.

## Slide 12: How the sizing table was derived
08 — Methodology
Fig 5. The derivation pipeline — countable signals in, a sized plan out, with adjustment factors refining the baseline before it becomes a commitment.
The tiers aren't arbitrary. Each threshold was reverse-engineered from where delivery effort tends to step-change on Fabric engagements, then cross-checked so the bands, the team shapes and the person-month estimates all reconcile with one another.
1 · Count signals
# source systems ingestion complexity
# Silver tables
# Gold KPIs
2 · Calibrate
to effort step-changes
Simple
4 · Apply modifiers
volume · quality · residency…
5 · Baseline plan
team + timeline + effort
worst-case dimension wins · MAX( )
Medium
Complex
3 · Bucket Into 3 Tiers

## Slide 13: How the sizing table was derived (Contd.)
Why these four dimensions
Count over judgement. All four are countable in discovery, before a line of code is written — so sizing is repeatable across estimators rather than a feel.
# Sources → ingestion effort. Each source is connector setup, authentication, incremental/CDC logic and source-to-target reconciliation.
Ingestion complexity → per-source difficulty. Batch, CDC and streaming are different skill sets and different effort classes for the same source count.
# Silver tables → transformation & modelling effort. Cleansing, conforming, SCD handling and DQ gates scale with table count.
# Gold KPIs → semantic & validation effort. Each KPI is a measure to build, a definition to agree with the business, and a number to validate.
How the bands were set & checked
Bands sit at effort step-changes. Simple = one squad can hold the whole solution; Medium = parallel workstreams plus a governance specialist; Complex = multiple pods plus a platform team and specialists (streaming, MDM).
Worst-case wins (MAX). One high-complexity dimension pulls the whole engagement up a tier, because it introduces workstreams and skills the lower tier's team can't absorb — the model deliberately errs against under-scoping.
Cross-checked against team × duration. Each tier's ranges were validated so that FTE × elapsed time reconciles with the stated person-month totals. The table is internally consistent, not three independent guesses.
Adjustment factors the four counts don't capture
Counts are proxies, not truth. Discovery applies these modifiers, which can nudge an engagement up a tier (and rarely down):
Data volume & velocity
Source data quality
Historical backfill depth
Consumer concurrency
Regulatory & data residency
Org & DataOps readiness
The size is a starting point, not a quote. Discovery counts the four signals → maps to a tier → the tier sets the baseline team, timeline and person-months → adjustment factors refine it → we confirm. A gnarly, SCD-heavy build of 20 tables can out-weigh 60 pass-through tables, which is precisely why the modifiers exist above the raw counts.

## Slide 14: Phased delivery — same seven workstreams, scaled per size
Governance, security, audit and DataOps run as continuous workstreams across the whole engagement rather than a trailing phase.
Simple — 8-week plan
W1
W8
 | w1 | w2 | w3 | w4 | w5 | w6 | w7 | w8
Mobilise & discovery |  |  |  |  |  |  |  | 
Platform & landing setup |  |  |  |  |  |  |  | 
Bronze ingestion |  |  |  |  |  |  |  | 
Silver transform + DQ |  |  |  |  |  |  |  | 
Gold + KPIs + model |  |  |  |  |  |  |  | 
Govern · secure · audit |  |  |  |  |  |  |  | 
Test · UAT · cutover |  |  |  |  |  |  |  | 
Discover
Workspaces · CICD · security base
Bronze
Sliver
Gold
Continuous
UAT + hypercare

## Slide 15: Phased delivery — same seven workstreams, scaled per size (Contd.1)
Governance, security, audit and DataOps run as continuous workstreams across the whole engagement rather than a trailing phase.
Medium — 14-week plan
W1
W14
 | w2 | w4 | w6 | w8 | w10 | w12 | w14
Discovery & blueprint |  |  |  |  |  |  | 
Platform & landing setup |  |  |  |  |  |  | 
Bronze ingestion |  |  |  |  |  |  | 
Silver transform + DQ |  |  |  |  |  |  | 
Gold + KPIs + model |  |  |  |  |  |  | 
Govern · secure · audit |  |  |  |  |  |  | 
Test · UAT · cutover |  |  |  |  |  |  | 
Discover
Foundation
Bronze
Sliver
Gold
Continuous
UAT + hypercare

## Slide 16: Phased delivery — same seven workstreams, scaled per size (Contd.2)
Complex — ~28-week plan (multi-wave)
W1
W28
 | w4 | w8 | w12 | w16 | w20 | w24 | w28
Discovery & architecture |  |  |  |  |  |  | 
Foundation + reuse framework |  |  |  |  |  |  | 
Bronze ingestion (waves) |  |  |  |  |  |  | 
Real-time / streaming (RTI) |  |  |  |  |  |  | 
Silver transform + DQ +MDM |  |  |  |  |  |  | 
Gold + KPIs + Semantic |  |  |  |  |  |  | 
Govern · secure · audit · DataOps |  |  |  |  |  |  | 
Geo roll-out (config-driven) |  |  |  |  |  |  | 
Test · UAT · cutover · hypercare |  |  |  |  |  |  | 
Discover + design
Eventstream · Eventhouse
Sliver waves
Gold + models
Geo 2..N onboarding
UAT + hypercare
Bronze waves
Platform · metadata framework
Continuous

## Slide 17: Dev → Test → Prod, under version control
06B — Environment Promotion
Every artefact — pipelines, notebooks, lakehouses, semantic models, reports — is versioned in Git and promoted through deployment pipelines. Environment differences are held in Variable Libraries and Key Vault, never hard-coded.
Deployment Pipeline · fabric-cicd · Fabric REST APIs
Fig 4. Environment promotion. Approval gates protect Test→Prod; Variable Libraries keep the code path identical while values change per stage.
Git repo
Azure DevOps / GitHub
branch per workspace
Dev
build & unit test
feature branches
Test
integration + DQ
UAT sign-off gate
Prod
monitored release
approval-gated
Variable
Libraries
+ Key Vault
config values differ per stage — artefacts stay identical